## Sheet1
Timeline for Minerals Plan Reg 19 consultation and submission
Note: Submission actions to be completed in detail following Reg 19 consultation
Week Commencing
Milestone description | Assigned to | time axis 2022-08-29 to 2023-10-30
Reporting | bar: 2023-03-20 to 2023-05-01
CMT confirm for forward plan date with Michelle Archer | MS | 2023-03-20: purdah
CMT 08/11/2022 (Joe B for approval, submission date & date of meeting) | MS | 2022-10-24: 24; 2022-10-31: 4; 2022-11-07: 8; 2023-03-20: purdah
CMT Cabinet meeting - (submission date & meeting date) | MS | 2022-11-07: 11; 2022-11-14: 16; 2023-03-20: purdah
JAC - report on progress and main changes | MS | 2022-12-19: 19; 2023-03-20: purdah
DCC Cabinet - forward plan deadline | MS | 2023-01-02: 3; 2023-03-20: purdah
Send Cabinet report to Jo Jackson by 29th to allow time for her to put on ModGov | MS | 2022-12-26: 29; 2023-03-20: purdah
DCC Cabinet - permission for Reg 19 consultation |  | 2023-01-30: 2; 2023-03-20: purdah
Send Full Council report to Jo Jackson by 27th Jan to allow time for her to put on ModGov |  | 2023-01-23: 27; 2023-03-20: purdah
DCC Full Council - permission for Reg 19 consultation | MS | 2023-02-13: 15; 2023-03-20: purdah
JAC - endorsement for Reg 19 consultation (TBC) |  | 2023-01-16: 16; 2023-03-20: purdah
Derby Executive Scrutiny | AW | 2023-02-06: ?; 2023-03-20: purdah
Derby Cabinet - permission for Reg 19 consultation | AW | 2023-02-13: 15; 2023-03-20: purdah
Derby City Full Council - permission for Reg 19 consultation (same report as Cabinet) | AW | 2023-02-27: 27; 2023-03-20: purdah
DCC Overview and Scrutiny committee (01/03/2023) | MS | 2023-02-20: 21; 2023-03-06: 1; 2023-03-20: purdah
LDS approval |  | 2023-02-20: 24; 2023-03-20: purdah
Reg 19 consultation | bar: 2023-03-20 to 2023-05-01
Draft Plan completion | All | 2023-01-09: n; 2023-03-20: purdah
Final internal consultation | All | 2023-03-20: purdah
Accessible background documents/development docs | AR | 2023-03-20: purdah
YouTube Video (agree timetable) | BW/Comms | 2023-03-20: purdah
Publicity (agree timetable) | CB/AW Comms | 2023-03-20: purdah
Consultation and documents put on line | CB/AW Comms | 2023-03-20: purdah
Paper copies on deposit? |  | 2023-01-30: ?; 2023-03-20: purdah
Organise consultation events/drop ins ??? | All | 2023-03-20: purdah
Dates of consultation events/drop ins ??? |  | 2023-03-20: purdah
Reg 19 consultation (6 weeks minimum) | All | 2023-02-27: 3; 2023-04-24: 30
Supporting documents
Report of Representations on 2021/2022 Consultation | All | bar: 2022-11-21 to 2022-12-05
Development Plan Scheme - update | MS | bar: 2023-01-16 to 2023-01-23
Statement of Community Involvement internal (+ check against Derby) | IG | bar: 2022-11-21
Local Aggregates Assessment - update | RS | bar: 2022-08-29 to 2022-10-31
Annual Monitoring Report (2019, 2020, 2021) - internal | AR/DH | bar: 2022-08-29 to 2022-09-26
Sustainability Appraisal - Final report - appoint Aecom | CB | bar: 2022-11-21 to 2022-12-05
Strategic Transport Assessment | CB | bar: 2022-11-21 to 2022-12-05
Habitats Regulations Assessment - Final report - appoint Aecom | VW | bar: 2022-11-21 to 2022-12-05
Strategic Flood Risk Assessment - Final report - appoint Aecom | DC | bar: 2022-11-21 to 2022-12-05
Health Impact Assessment - internal | RB | bar: 2022-11-21 to 2022-12-05
Equalities Impact Assessment - internal | SJ | bar: 2022-11-21 to 2022-12-05
Heritage Impact Assessment - commission | RS | bar: 2022-09-19 to 2022-09-26
Production of Heritage Impact Assessment | bar: 2022-10-10 to 2022-10-31
Chapter 2 - Spatial Overview
Update chapter | IG
Update background paper | IG
Chapter 3 - Strategic priorities: Vision and Objectives
Update chapter | All
Update development paper | All
Respond to schedule of reps | All
Chapter 4 - Sustainable Minerals Development
Update chapter | CB
Update development paper | CB
Respond to schedule of reps | CB
Chapter 5 - Climate Change
Update chapter | CB
Update background paper | CB
Update development paper | CB
Respond to schedule of reps | CB
Chapter 6.1 - Secondary and Recycled Aggregates
Update chapter | RS
Update background paper | RS
Update development paper | RS
Respond to schedule of reps | RS
Update S of CG (Issue 1) | RS
Chapter 6.2 - Sand and Gravel
Update chapter | RS
Update background paper | RS
Update development paper | RS
Respond to schedule of reps | RS
Update S of CG (Issue 2 ) | RS
Chapter 6.3 - Crushed Rock
Update chapter | RS
Update background paper | RS
Update development paper | RS
Respond to schedule of reps | RS
Update S of CG (Issue 3) | RS
Chapter 6.4 - Reducing the supply of aggregates from the PDNP
Update chapter | RS
Update background paper | RS
Update development paper | RS
Respond to schedule of reps | RS
Update S of CG (Issue 4) | RS
Chapter 7.1 - Building Stone
Update chapter | RS
Update background paper | RS
Update development paper | RS
Respond to schedule of reps | RS
Update S of CG (Issue 5) | RS
Chapter 7.2 - Industrial Limestone
Update chapter | CB
Update background paper | CB
Update development paper | CB
Respond to schedule of reps | CB
Update S of CG (Issue 6 - industrial dolomite Whitwell) | CB
Update S of CG (Issue 7 - Aldwark South extension) | CB
Update S of CG (Issue 8 - Hope cement works) | CB
Update S of CG (Issue 9 - Tunstead cement works) | CB
Chapter 7.3 - Brick Clay and Fireclay
Update chapter | CB
Update background paper | CB
Update development paper | CB
Respond to schedule of reps | CB
Update S of CG (Issue 10 - Mouselow) | CB
Update S of CG (Issue 11 - Waingroves) | CB
Chapter 7.4 - Vein Minerals
Update chapter | CB
Update background paper | CB
Update development paper | CB
Respond to schedule of reps | CB
Update S of CG (Issue 12) | CB
Chapter 8.1 - Coal and Colliery Spoil
Update chapter | VW
Update background paper | VW
Update development paper | VW
Respond to schedule of reps | VW
Update S of CG (Issue 13 - deep mined & surface coal) | VW
Chapter 8.2 - Hydrocarbons
Update chapter | CB/VW
Update background paper | CB/VW
Update development paper | CB/VW
Respond to schedule of reps | CB/VW
Update S of CG (Issue 14) | CB/VW
Chapter 9.1 - Safeguarding Mineral Resources
Update chapter | RS
Update background paper | RS
Update development paper | RS
Respond to schedule of reps | RS
Update S of CG (Issue 15) | RS
Chapter 9.2 - Safeguarding Mineral Infrastructure
Update chapter | RS
Update background paper | RS
Update development paper | RS
Respond to schedule of reps | RS
Update S of CG (Issue 16) | RS
Chapter 10 - Restoration of sand and gravel sites in the the river valleys
Update chapter | RS
Update development paper 11 | RS
Respond to schedule of reps | RS
Update S of CG (Issue 17 - TV restoration strategy) | RS
Chapter 11 - Development Management
Update chapter | VW
Update development paper 12 | VW
Respond to schedule of reps | VW
Chapter 12 - Monitoring and Implementation
Update chapter | RS (CB)
Respond to schedule of reps | RS (CB)
Background Paper 11 - Cumulative Impacts
Update chapter | CB/VW
Update background paper | CB/VW
Appendix A
Update site allocations requirements | RS (CB)
Update maps | ?
Appendix B
Update operational sites information | RS
Appendix C
Check Saved Policies to be replaced | RS
Appendix D
Update document list for Reg 19 | RS
Duty to Cooperate
Review DtC Intro and Overview | CB
Statement of Common Ground
Finalise SofCG and check issues | All
Glossary
Update | AC
Minerals Plan submission (to be finalised following Reg 19)
Approval to submit (DCC) - awaiting publication of 2023/24 committee dates
Approval to submit (Derby City) - awaiting publication of 2023/24 committee dates
Submit to S of S | bar: 2023-10-30
Production of Minerals Plan formal submission notice
Print copies for deposit in LPA/DCC receptions etc
Put submission plan on DCC website & link from Derby City website
Appoint programme officer
Book EiP rooms
Key
Actions | bar: 2022-08-29
Meeting | bar: 2022-08-29
Milestone | bar: 2022-08-29
Note on K8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: submit to Joe B
Note on AB20: Alison Richards (Place): Report to Danny Sutherland by 21st Feb

## Sheet2
Milestone description | Assigned to | [46 empty] | Jan 2024 | Feb 2024 | Mar 2024 | April 2024 | May 2024 | June 2024 | July 2024 | Aug 2024 | Sept 2024 | Oct 2024 | Nov 2024 | Dec 2024 | time axis 2022-12-19 to 2023-10-30
Reporting | bar: 2023-03-20 to 2023-05-01
JAC - report on progress and main changes | MS | 2022-12-19: 19; 2023-03-20: purdah |  |  |  |  | purdah
JAC - endorsement for Reg 19 consultation (TBC) | MS | 2023-01-09: 9 or 10; 2023-03-20: purdah |  |  |  |  | purdah
Derby Executive Scrutiny | AW | 2023-01-09: 10; 2023-03-20: purdah |  |  |  |  | purdah
Derby Cabinet - permission for Reg 19 consultation | AW | 2023-01-09: 11; 2023-03-20: purdah |  |  |  |  | purdah
Derby Council - permission for Reg 19 consultation | AW | 2023-01-16: 18; 2023-03-20: purdah |  |  |  |  | purdah
DCC Cabinet - permission for Reg 19 consultation | MS | 2023-01-30: 2; 2023-03-20: purdah |  |  |  |  | purdah
DCC Full Council - permission for Reg 19 consultation | MS | 2023-02-13: 15; 2023-03-20: purdah |  |  |  |  | purdah
DCC Overview and Scrutiny committee (01/03/2023) | MS | 2023-03-06: 1; 2023-03-20: purdah |  |  |  |  | purdah
Reg 19 consultation 8 weeks | All | 2023-02-13: 17; 2023-04-03: 14; 2023-04-10: purdah
JAC - Endorsement to submit to S of S | MS/AW
DCC CMT Cabinet - Approval to submit to S of S | [53 empty] | 12
DCC Cabinet - Approval to submit to S of S | MS | [54 empty] | 12
DCCFull Council - Approval to submit to S of S | [56 empty] | 10
Derby - Approval to submit to S of S - delegated | AW
Submit to S of S for examination Reg 22 (final date) | All | [56 empty] | 30 | bar: 2023-10-30
Indicative timetable
Examination period (Reg 24) | PINS
JAC - Endorsement to adopt | MS/AW
DCC Cabinet/Full Council - Approval to adopt | MS
Derby - Cabinet/Full Council - Approval to adopt | AW
Adoption Reg 26 | MS
Challenge period

## EIP
Timetable for Derbyshire and Derby Minerals Local Plan Examination in Public
Milestone description | Assigned to | 2025-07-07 | 2025-07-14 | 2025-07-21 | 2025-07-28 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2025-05-04 | 2025-05-11 | 2026-05-18 | 2026-05-25 | 2025-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18
Inspector issues letter (approx) | PINS | [8 empty] | 5 Sept
Modifications
Policy and supporting text wording | AS / CW
Discussions with PDNP | SB
Discussions with East Midlands Aggregate Group | SB / AS
Landbank calculations/production capacity assessment | AS
Policies Map | AS / IG
Updated Modifications Schedule | AS / CW
Commissioned work
Sequential Flood Test | SB / AS
Site Assessment post Sequential Test | SB / AS
Summary Paper on Site Assessment Methodology | SB / AS
Sustainability Appraisal | SB / AS
Draft Report to DCC Committee Services to seek approval to consult on the above | SB
Report presented to Cabinet Approval to consult on above and other Mods | SB | [41 empty] | Cabinet tbc
Inspectors consideration of proposed consultation documents
Consultation in relation to the above
Statement of Common Ground
Minerals Product Association | SB / AS
Local Development Scheme
Draft Report to DCC Committee Services | SB
Draft JAC Report to be submitted to DCC Committee Services | SB
Cabinet Member Report to be drafted by Derby City Council Officers | SB
Report to be presented to Derbyshire and Derby Minerals and Waste Joint Advisory Committee. | PC
Report to be presented to Derby City Council Cabinet Member | SB/PC
Publish updated LDS to website | CW
Submitting Main Modifications to PINS
Main Modifications consultation period | AS/CW
Report on Main Modification consultation results | SB/AS
Additional hearing session
Final Main Modifications submitted to PINS
Final public consultation
Final submission to PINS | SB
Anticipated Inspectors Report (approx) | PINS
Draft Report to Cabinet with recommendation to adopt Plan | SB/PC
Present Report to Cabinet to recommend adoption | SB/PC | [75 empty] | Cabinet tbc
Draft Report to Full Council to recommend adoption of Plan | SB/PC
Present Report to Full Council to recommend adoption of Plan | SB/PC | [77 empty] | Full Council tbc