## Plan period trajectory
Site number | Site | Number of units | Application reference | Application/permission date | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2035-36 | 2036-37 | 2037-38 | 2038-39 | 2039-40 | 2040-41 | 2041-42 | 2042 onwards | Notes
| Houlton | 4298 |  |  | 124 | 121 | 168 | 160 | 230 | 250 | 229 | 210 | 210 | 199 | 170 | 170 | 170 | 170 | 170 | 170 | 140 | 1237
| Care Home Houlton, land N of Handley Rd | 28 | R25/0653 | 2025-11-20 | 2027-28: 28 |  | Full permission for 66 bed C2 care home. Divided by 2.4 = 28 homes equivalent
| Parcel 14, Key Phase 1, Houlton RUGBY, CV23 0AS | 82 | R26/0203 | 2026-03-10 | 2027-28: 40; 2028-29: 42 |  | RM awaiting determination
| Parcel 23 (Morris Homes), Houlton (Rugby Radio Station), Key Phase 4, Watling Street, Rugby, CV23 0AS | 78 | R26/0327 | 2026-04-17 | 2027-28: 40; 2028-29: 38 |  | RM awaiting determination
| Key Phase Four - Parcel E (Miller Homes) R25/0549 - 216 Units | 216 | R25/0549 | 2025-06-20 | 2026-27: 37; 2027-28: 40; 2028-29: 40; 2029-30: 40; 2030-31: 40; 2031-32: 19 |  | Full planning permission
| Parcel B (Dandara), Key Phase 4, Houlton | 289 | R26/0682 | currently being validated | 2027-28: 20; 2028-29: 40; 2029-30: 40; 2030-31: 40; 2031-32: 40; 2032-33: 40; 2033-34: 40; 2034-35: 29 |  | RM awaiting determination
| Key Phase Two - Parcel A (Francis Jackson Homes) R21/1099 31 units | 9 | R21/1099 | 2022-09-12 | 2025-26: 6; 2026-27: 3 |  | Under construction
| Key Phase Three - Parcels A and B (Redrow) R18/1177, R19/1375, R20/0709, R21/0739 - 248 Units | 35 | R18/1177, R19/1375, R20/0709, R21/0739 | 2018-12-21 | 2025-26: 25; 2026-27: 10 |  | Under construction
| Key Phase Three - Parcels C and F (William Davis) R20/0681 - 146 Units | 82 | R20/0681 | 2021-04-01 | 2025-26: 48; 2026-27: 34 |  | Under construction
| Key Phase Three - Parcel D (Mulberry Homes) R21/0873 - 147 units | 82 | R21/0873 | 2022-04-11 | 2025-26: 45; 2026-27: 37 |  | Under construction
| Remainder of Houlton allocation | 3397 |  | 2014-05-21 |  |  |  |  | 150 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 170 | 140 | 1237 | Outline planning permission
| South West Rugby | 3900 |  |  | 0 | 20 | 40 | 40 | 80 | 120 | 368 | 338 | 338 | 313 | 298 | 268 | 248 | 263 | 278 | 255 | 238 | 395
| Coventry Road (Miller Homes) | 210 | R18/0936, R24/0971 | 2022-12-23 | 2026-27: 20; 2027-28: 40; 2028-29: 40; 2029-30: 40; 2030-31: 40; 2031-32: 30 |  | Detailed planning permission
| Cawston Farm 1 (Tritax Symmetry) (parcel 12, plot T2) | 275 | R18/0995 | Submitted 16/05/2019 | 2029-30: 20; 2030-31: 40; 2031-32: 40; 2032-33: 40; 2033-34: 40; 2034-35: 40; 2035-36: 40; 2036-37: 15 |  | Outline planning application awaiting determination.
| Cawston Farm 2 (Tritax Symmetry)(Parcel 12, Plot T3) | 350 | R22/0853 | Submitted 26/08/2022 | 2031-32: 40; 2032-33: 40; 2033-34: 40; 2034-35: 40; 2035-36: 40; 2036-37: 40; 2037-38: 40; 2038-39: 40; 2039-40: 30 |  | Outline planning application awaiting determination.
| Land south west of Cawston Lane (Catesby Estates) | 470 | R25/0487 | submiutted 02/06/2025 | [6 empty] | 50 | 50 | 50 | 50 | 50 | 45 | 40 | 40 | 50 | 25 | 20 |  | Current Application - Outline Application R25/0487 (Awaiting determination)
| Land to the North East of Cawston Lane & Land to the East of Alwyn Road (Taylor Wimpey TW1 to 4 and 5) | 800 | R25/0407 | submitted 01/05/2025 | [6 empty] | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 100 | 88 |  | Current Application- Outline Application R25/0407 (Awaiting determination)
| Land East and West of Cawston Lane, North of Coventry Road and Land East of Alwyn Road (Homes England) | 1600 | R25/0491 | submitted 05/06/2025 | [6 empty] | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 115 | 130 | 130 | 130 | 395 | Current Application- Outline Application R25/0491 (Awaiting determination)
| Land South of Montague Road, Bilton (Taylor Wimpey) R25/0979 | 195 | R25/0979 | 2025-12-03 | 2029-30: 20; 2030-31: 40; 2031-32: 40; 2032-33: 40; 2033-34: 40; 2034-35: 15 |  | Full planning application awaiting determination
| Eden Park | 602 |  |  | 52 | 0 | 25 | 55 | 55 | 55 | 55 | 55 | 50 | 50 | 50 | 50 | 50
| Eden Park Phase R3 (Bloor Homes) | 52 | R19/0976 | 2020-08-20 | 2025-26: 52 |  | complete
| Eden Park Phases R5, R6, and R7 (Bloor Homes) | 550 | R23/0453 | 2013-08-20 |  |  | 25 | 55 | 55 | 55 | 55 | 55 | 50 | 50 | 50 | 50 | 50 | [5 empty] | Outline planning permission, final reserved matters determined 15th Jan 2025.
| 2019 Local Plan Main Rural Settlements Allocations | 205 |  |  | 2025-26: 102; 2026-27: 63; 2027-28: 0; 2028-29: 0; 2029-30: 0; 2030-31: 0; 2031-32: 0; 2032-33: 0; 2033-34: 25; 2034-35: 15
| Wolvey Campus, Wolvey (Countryside Properties) | 90 | R20/0968, R22/0113 | 2022-08-25 | [18 empty] | Complete | bar: 2025-26
| Land at Coventry Road, Wolvey (O'Flanagan Homes) | 11 |  | 2024-03-27 | 2025-26: 0; 2026-27: 11 |  | Full planning permission.
| Land North of Coventry Road, Long Lawford (Bloor Homes) | 149 | R17/1089 | Appeal Approved 01/09/2021 | 2025-26: 85; 2026-27: 13 |  | Under construction
| Land off Squires Road, Stretton on Dunsmore | 55 | R17/1767 R24/0289 | 2022-04-26 | 2025-26: 16; 2026-27: 39 |  | Under construction
| Plott Lane, Stretton on Dunsmore | 25 |  |  | 2033-34: 25 |  | Application not yet received, alocated for 25 units, prior application refused 25.02.2021
| Linden Tree Bungalow, Wolston | 15 |  |  | 2034-35: 15 |  | Application not yet received, allocated for 15 units
| Current Permissions & Prior Approvals as of 1 April 2025 | 723 |  |  | 205 | 174 | 154 | 40 | 28 | 0 | 24 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Land North of Ashlawn Road (Barratt) | 216 | R21/0689 | 2022-03-23 | 2025-26: 30 |  | Under construction
| Land North of Ashlawn Road, (David Wilson) | 206 | R20/0124 | 2021-12-21 | 2025-26: 79; 2026-27: 1 |  | Under construction
| Former Newton Vehicle Rentals Site, 117 Newbold Road | 122 | R17/2113, R19/0902 R19/1496 R23/0357 R23/0817 | 2020-08-20 | 2031-32: 24; 2032-33: 98 |  | Full planning permission but understood not now being commenced. See PINS proforma.
| Land North of Projects Drive, Rugby | 108 | R24/0103 | 2025-06-26 | 2027-28: 40; 2028-29: 40; 2029-30: 28 |  | under construction
| Dipbar Fields, Dunchurch (Persimmon Homes) | 86 | R13/0690, R19/1047 | 2023-06-20 | 2025-26: 27; 2026-27: 38; 2027-28: 21 |  | Full planning permission
| Wolston Allotments, Stretton Road, Wolston (Spitfire Homes) | 48 | R19/1411 R22/0201 | 2023-03-31 | 2025-26: 4 |  | complete
| BRINKLOW MARINA, CATHIRON LANE, BRINKLOW, RUGBY, CV23 0JH | 30 | R24/0936 | 2026-03-26 | 2025-26: 30 |  | complete
| Binley Woods Servic Centre | 28 | R22/0207 | 2024-09-11 | 2025-26: -1; 2027-28: 28 |  | Demolition carried out
| 32 High Street, Rugby, CV21 3BW | 27 | R21/0894 R25/0022 R25/0127 | 2022-12-13 | 2025-26: 27 |  | Under construction
| Former Inwoods House, Ashlawn Road, Dunchurch | 25 | R23/0491 R24/0327 | 2024-03-20 | 2025-26: 0; 2026-27: 8; 2027-28: 17 |  | under construction
| Yum Yum World Ltd, 4 High Street, Rugby, CV21 3BG | 21 | R17/0967 | 2019-04-03 | 2025-26: 0; 2026-27: 16 |  | Under construction
| Land South East of Brownsover Lane, Brownsover Lane (Jelson Homes) | 14 | R14/1941 (R22/0449) | 2020-04-08 | 2025-26: 9 |  | complete
| Elms Farm, Oxford Road, Marton, CV23 9RQ | 11 | R21/0469 R21/0470 (LB) | 2023-07-12 | 2025-26: 0; 2026-27: 11 |  | Full planning permission - pre commencement conditions discharged
| 25 Barby Lane, Rugby, CV22 5QJ | 11 | R24/0474 | 2026-03-12 | 2027-28: 11 |  | full planning permission
| Development Land at Pailton Radio Station, Montilo Lane, Pailton, CV23 0HD | 10 | R21/0937 & R24/0920 | 2021-11-08 | 2026-27: 10 |  | Full planning permission
| 16-20 Lawford Road, Rugby, CV21 2DY | 10 | R15/1520, R21/0930 | 2022-05-12 | 2026-27: 10 |  | Under construction
| First Floor 7-8 Church Street, Rugby, CV21 3PH | 10 | R22/0479 | 2022-11-09 | 2026-27: 10 |  | Under construction
| Land West Side of Heritage Close, Rugby | 10 | R22/0383 R24/0064 | 2023-12-06 | 2026-27: 10 |  | Full planning permission
| Land on the south side of Spring Street | 9 | R23/1115 | 2025-04-11 | 2026-27: 9 |  | Full planning permission
| 1-2, ST MATTHEWS STREET, RUGBY, CV21 3BY | 9 | R25/0238 | 2025-07-21 | 2027-28: 9 |  | Full planning permission
| 76 Buchanan Road, Bilton | 8 | R18/0830, R21/0963 R25/0031 | 2018-11-22 | 2026-27: 8 |  | Under construction
| Rugby Business Centre, 21-23 Clifton Road, Rugby, CV21 3PY | 8 | R24/0829 | 2024-12-19 | 2026-27: 8 |  | Full planning permission
| Land To The Rear Of 150, Railway Terrace, Rugby | 8 | R25/0421 | 2025-10-15 | 2027-28: 8 |  | Full planning permission
| 7 & 8 St Matthews Street, Rugby, CV21 3BY | 7 | R20/1092 | 2021-02-19 | 2026-27: 4 |  | complete
| Land at Manor Farm, Hinckley Road, Burton Hastings. CV11 6RG | 6 | R17/2041, R21/1037, R22/0260, R22/0701, R22/0844, R22/0985 | 2022-12-22 | 2026-27: 6 |  | Full planning permission, demolition completed
| The Malthouse, Main Street, Thurlaston | 6 | R21/0477 (R25/0090) | 2022-06-30 | 2026-27: 6 |  | under construction
| 2-3 High Street, Rugby, CV21 3BG | 6 | R23/0722 | 2024-03-27 | 2026-27: 6 |  | under construction
| Rugby Business Centre, 21-23 Clifton Road, Rugby, CV21 3PY | 6 | R23/0812 | 2024-07-12 | 2026-27: 6 |  | Full planning permission
| 11-12 Sheep Street, Rugby, CV21 3BU | 5 | R22/0979, R26/0323 | 2023-07-03 | 2026-27: 5 |  | Full planning permission
| Drayton House, Southam Road, Dunchurch, Rugby, CV22 6NL | 5 | R25/0297 | 2025-12-24 | 2027-28: 5 |  | full planning permission
| 140 Railway Terrace, Rugby, CV21 3HN | 5 | R24/0533 | 2023-06-14 | 2027-28: 5 |  | full planning permission
| 92-93, COVENTRY ROAD, DUNCHURCH, RUGBY, CV22 6RE | 5 | R24/1090 | 2025-06-05 | [18 empty] | Outline planning permission approved but reserved matters withdrawn unclear if coming forward
| FISHPOOLS FARM, MAIN STREET, FRANKTON, RUGBY, CV23 9PB | 5 | R25/0590 | 2025-09-01 | 2027-28: 5 |  | full planning permission
| Land North Of, Post Office Road, Leamington Hastings | 5 | R25/0432 | 2025-07-10 | 2027-28: 5 |  | full planning permission
| 15 Bilton Lane, Rugby | 5 | R19/1309 (R21/0353, R21/0451, R22/0125) | 2021-05-17 | 2026-27: 2 |  | Under construction
| Windfalls for sites of <5 dwellings |  |  |  | 22 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 2025/26 is a net figure, includes 8 demolitions
| total existing supply |  |  |  | 505 | 428 | 437 | 345 | 443 | 475 | 726 | 751 | 673 | 627 | 568 | 538 | 518 | 483 | 498 | 475 | 428 | 1682
Site Ref. | New allocations | 2850 |  |  |  |  | 0 | 189 | 195 | 360 | 350 | 384 | 312 | 329 | 336 | 146 | 124 | 105 | 20 | 0 | 0 | 0
6 | Land east of Fosse Way, Stretton-on-Dunsmore | 3 | N/A | Assumed 2027/2028 | 2029-30: 3
39 | Dyers Lane, Wolston | 15 | N/A | Assumed 2027/2028 | 2029-30: 5; 2030-31: 5; 2031-32: 5
54 | Oakdale Nursery, Brandon | 43 | R24/0716 | Approved Feb 2026 | 2028-29: 20; 2029-30: 20; 2030-31: 3
59 | Newton Manor Lane, Brownsover | 285 | N/A | Expected 2026/2027 | 2029-30: 40; 2030-31: 40; 2031-32: 40; 2032-33: 40; 2033-34: 40; 2034-35: 40; 2035-36: 45
62 | Morgan Sindall House, Corporation Street, Rugby | 90 | R26/0501 | Validated May 2026 | 2028-29: 54 |  | Prior approval application awaiting determination, assumed 2 years to completion. Application is only for 54 dwellings
81 | Land west of Fosse Way, Stretton-on-Dunsmore | 40 | N/A | Expected 2026/2027 | 2028-29: 20; 2029-30: 20
87 | Hillcrest Farm, Newton | 25 | N/A | Assumed 2027/28 | 2030-31: 20; 2031-32: 5
100 | Land at High St., Ryton-on-Dunsmore | 37 | N/A | Assumed 2027/28 | 2029-30: 10; 2030-31: 27 |  | Neighbourhood plan allocation. Appeal dismissed on R22/1120
129 | Land north of Lilbourne Road, Clifton upon Dunsmore | 60 | N/A | Expected 2026/2027 | 2028-29: 40; 2029-30: 20
136 | Land North of Warwick Road, Wolston | 80 | N/A | Assumed 2027/28 | 2030-31: 20; 2031-32: 20; 2032-33: 20; 2033-34: 20
153 | Westway Car Park, Rugby | 24 | N/A | Expected 2030/31 | 2032-33: 24
172 | Elizabeth Way, Long Lawford | 5 | N/A | Assumed 2031/32 | 2033-34: 5
202 | Newton Road, Clifton upon Dunsmore | 80 | N/A | Expected 2026/2027 | 2028-29: 20; 2029-30: 20; 2030-31: 20; 2031-32: 20
253 | Lawford Fields Farm, Long Lawford | 250 | N/A | Expected 2026/2027 | 2030-31: 50; 2031-32: 50; 2032-33: 50; 2033-34: 50; 2034-35: 50
279 | Stagecoach Depot Car Park, Railway Terrace, Rugby | 32 | N/A | Assumed 2032/33 | 2035-36: 20; 2036-37: 12
283 | Rugby Central Shopping Centre | 200 | R22/0657 | Approved Feb 2026; Assumed new application 2030/31 | 2034-35: 99; 2035-36: 101 |  | Full planning permission required to commence by 2027. Assumed new application before implementation. Demolition and site clearance needed first. Assumed that one block would be completed at a time
294 | Land adjacent to 9 Railway Terrace, Rugby | 14 | N/A | Assumed 2035/36 | 2037-38: 14
307 | North Road, Clifton upon Dunsmore | 10 | N/A | Assumed 2027/2028 | 2029-30: 10
309 | Land north of B4109, Wolvey | 150 | N/A | Expected 2026/27 | 2030-31: 50; 2031-32: 50; 2032-33: 50
315 | Land south of Rugby Road, Brinklow | 250 | N/A | Expected 2027/2028 | 2030-31: 40; 2031-32: 40; 2032-33: 40; 2033-34: 40; 2034-35: 40; 2035-36: 50
316 | Land at Long Lawford | 400 | N/A | Expected 2027/2028 | 2031-32: 50; 2032-33: 50; 2033-34: 50; 2034-35: 50; 2035-36: 50; 2036-37: 50; 2037-38: 50; 2038-39: 50
332 | Albert Street, Rugby | 25 | N/A | Expected 2028/29 | 2030-31: 25
337 | West Farm and Home Farm, Brinklow | 75 | N/A | Assumed 2031/32 | 2035-36: 20; 2036-37: 20; 2037-38: 20; 2038-39: 15
338 | Land south of Crick Road, Houlton | 250 | N/A | Expected 2027/28 | 2032-33: 50; 2033-34: 50; 2034-35: 50; 2035-36: 50; 2036-37: 50
348 | The Croft, Stretton-on-Dunsmore | 70 | N/A | Expected 2026/2027 | 2028-29: 20; 2029-30: 20; 2030-31: 20; 2031-32: 10
349 | Land rear of 30 Albert Street, Rugby | 5 | N/A | Assumed 2031/32 | 2033-34: 5
350 | Rounds Gardens South, Rugby | 70 | N/A | Expected 2027/2028 | 2030-31: 20; 2031-32: 20; 2032-33: 20; 2033-34: 10
351 | Rounds Gardens North, Rugby | 60 | N/A | Expected 2026/2027 for 100+ units | 2031-32: 20; 2032-33: 20; 2033-34: 20
352 | Former Snooker Hall, Railway Terrace, Rugby | 7 | N/A | Assumed 2031/32 | 2033-34: 7
353 | Town Hall, Rugby | 114 | N/A | Assumed 2033/34 | 2036-37: 14; 2037-38: 40; 2038-39: 40; 2039-40: 20
354 | 92 Lower Hillmorton Road, Rugby | 34 | R26/0155 | Approved June 2026 | 2028-29: 15; 2029-30: 19 |  | Full planning permission granted June 2026
355 | Land adjacent to 44 Craven Road, Rugby | 5 | N/A | Assumed 2031/32 | 2033-34: 5
356 | The Railings, Rugby | 10 | N/A | Assumed 2031/32 | 2033-34: 10
357 | 28-29 High Street, Rugby | 8 | N/A | Assumed 2031/32 | 2029-30: 8
358 | Land at Coventry Road, Wolvey | 60 | N/A | Expected 2026/27 | 2030-31: 20; 2031-32: 20; 2032-33: 20
| TOTAL TRAJECTORY |  |  | Assume planning applicatiTOTAL in 2027/28 | 505 | 428 | 437 | 534 | 638 | 835 | 1076 | 1135 | 985 | 956 | 904 | 684 | 642 | 588 | 518 | 475 | 428 | 1682
Main omission sites
73 | Lodge Farm | 2680 |  | assume 2028/29 | 2035-36: 150; 2036-37: 150; 2037-38: 180; 2038-39: 180; 2039-40: 180; 2040-41: 180; 2041-42: 180 | 180 | Based on Start to Finish
114 | Land at M6 Junction1, Newbold on Avon and Long Lawford | 3000 |  | assume 2028/29 | 2035-36: 150; 2036-37: 150; 2037-38: 180; 2038-39: 180; 2039-40: 180; 2040-41: 180; 2041-42: 180 | 180 | Based on Start to Finish

## Annual & cumulative completions
| 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2035-36 | 2036-37 | 2037-38 | 2038-39 | 2039-40 | 2040-41 | 2041-42
Projected completions in year | 505 | 428 | 437 | 534 | 638 | 835 | 1076 | 1135 | 985 | 956 | 904 | 684 | 642 | 588 | 518 | 475 | 428
Cumulative completions | 505 | 933 | 1370 | 1904 | 2542 | 3377 | 4453 | 5588 | 6573 | 7529 | 8433 | 9117 | 9759 | 10347 | 10865 | 11340 | 11768

## Trajectory bar chart
| 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2035-36 | 2036-37 | 2037-38 | 2038-39 | 2039-40 | 2040-41 | 2041-42
Requirement | 636 | 636 | 636 | 636 | 636 | 636 | 636 | 636 | 636 | 636 | 636 | 636 | 636 | 636 | 636 | 636 | 636
Projected completions in year | 505 | 428 | 437 | 534 | 638 | 835 | 1076 | 1135 | 985 | 956 | 904 | 684 | 642 | 588 | 518 | 475 | 428

## 5yhls calculation at 1 Apr 28
Five year supply calculation 2028-2033
A | Base target (636 x 5) | 3180
B | Projected shortfall 2025-2028 | 538
C | 5 year requirement (A + B) | 3718
D | Plus 5% buffer (C x 1.05) | 3904
E | Annualised requirement (D ÷ 5) | 780.8
F | Projected supply | 4218
G | No. of years' supply (F ÷ E) | 5.4022